## Intro
Gantt chart, project milestones and deliverables, RACI matrix are presented in 3 separate lists.

## Gantt diagram
Gantt diagram
| Start |  |  |  |  | Finish
| 2024-09-19 |  |  |  |  | 2024-10-24
Phase/ Month | 1 |  |  |  | 2
week | 1 | 2 | 3 | 4 | 5
Requirements analysis and planning
UI/UX protype
Configuring the Database
Deployment plan
Back-end development
Front-end development
Development and training of a model based on user data
Testing web-application
Project Management
|  |  | 2024-10-03 |  | 2024-10-17 | 2024-10-24
|  |  | -Business Requirements Document (BRD). -Design UI/UX(figma link). -Approved Project Mangement Paln. -Technical Requerments (staging) - ERD - Architechture - Prototype of web-application |  | - API specification - Code of web-application - ML model | - Guide of deployment - Web-application

## RACI Matrix
Career Buddy
| ML Engineer | UX/UI Designer | Data Engineer | Front-end | Back-end
| Designs and develops a machine learning model. Responsible for developing and implementing algorithms for the forecasting system. | Focused on creating user-centric design, responsible for the look, feel, and functionality of a digital interface. | Creates and maintains data pipelines to ensure data is collected, stored, and processed. Responsible for creating an architecture that provides easy access to clean and reliable data for the machine learning engineer. | Designs the user side of apps, ensuring the interface is responsive, accessible, and interactive. Works with UX/UI Designer to bring visual elements to life, ensuring a seamless user experience across devices. | Focuses on the server-side business logic and APIs that power applications. Provides infrastructure-side execution of business logic, allowing seamless interaction between front-end and back-end systems
| Anisin Aleksandr | Anisin Aleksandr | Tyukavkina Ekaterina | Dandamaev Gadji | Malysh Igor
Requirements analysis and planning | C | AR | C | C | C
UI/UX protype |  | AR | I | C | I
Configuring the Database
Define entities and relationships |  |  | AR |  | C
Design an ER diagram |  |  | AR |  | C
Deploy PostgreSQL |  |  | AR |  | C
Load data to DB using ETL script |  |  | AR |  | C
Deployment plan
Deploy DB | C |  | C | C | AR
Organize access to a remote server | C |  | C | C | AR
Create Dockerfile for Backend | C |  | C | C | AR
Create Dockerfile for Frontend | C |  | C | C | AR
Create Dockercompose | C |  | C | C | AR
Back-end development
Development of API for registration and authentication | C |  | C | C | AR
Development of API for dashboard page | C |  | C | C | AR
Developing interaction with ML | C |  | C | C | AR
Configuring interaction with the frontend part | C |  | C | C | AR
Front-end development
Development of registration and authentication pages |  | C |  | AR | C
Creating a dashboard page |  | C |  | AR | C
Performance optimization |  | C |  | AR | C
Configuring interaction with the backend part |  | C |  | AR | C
Development and training of a model based on user data
Data acquisition | AR |  | C
Model Selection | AR |  | C
Model Training | AR |  | C
Model Evaluation | AR |  | C
Model Deployment | AR |  | C
Testing web-application | C | C | C | C | AR
Project Management | I | AR | I | I | I

## Project Milestones and Delivera
Phase | Start Date | End Date | Deliverables
Requirements analysis and planning | 2024-09-19 | 2024-09-25 | Requirements document, project plan
UI/UX prototype | 2024-09-26 | 2024-10-02 | UI/UX design prototypes
Configuring the Database | 2024-09-26 | 2024-10-02 | Database schema, initial configuration
Deployment plan | 2024-09-26 | 2024-10-24 | Deployment strategy document
Back-end development | 2024-09-26 | 2024-10-16 | Completed back-end codebase
Front-end development | 2024-09-26 | 2024-10-16 | Completed front-end codebase
Development and training of a model based on user data | 2024-10-03 | 2024-10-16 | Trained model, initial results
Testing web-application | 2024-09-26 | 2024-10-16 | Test reports, bug resolution logs
Project Management | 2024-09-19 | 2024-10-24 | Progress reports, communication logs